26 March 2012

[7-12]

Administrative Assessment Report – Proposal M1008

Maximum Residue Limits (2012)

| Date completed (proposal prepared): 15 March 2012 |  |  |
| --- | --- | --- |
| Brief Description of Proposal: To consider varying certain maximum residue limits for residues of agricultural or veterinary chemicals that may occur in food. |  | Potentially affected Standard: Standard 1.4.2 |
| Procedure: General | Estimated total hours: Maximum 650 hours Reasons why: Varying maximum residue limits | Estimated start work: March 2012 |

Other Comments or Relevant Matters: This Proposal will consider varying certain maximum residue limits (MRLs) in the Australia New Zealand Food Standards Code (the Code). This is a routine process, both to allow the sale of food with legitimate residues and to remove limits that are no longer required. This Proposal may include consideration of MRL variations requested by the Australian Pesticides and Veterinary Medicines Authority, as well as other interested parties.

## DECISION

Proposal prepared Date: 15 March 2012

CONSULTATION & ASSESSMENT TIMEFRAME

Proposed length of public consultation period: 4 weeks

Proposed Timeframe for Assessment: Commence Assessment (clock start) Mid-March 2012 Completion of Assessment Early June 2012 Public comment Mid-June – Mid-July 2012 Board to complete Approval Mid-September 2012 Notification to Ministerial Council Late September 2012 Anticipated gazettal if no review requested Early December 2012