

**3 June 2014**

**[10–14]**

**Administrative Assessment Report – Proposal P1033**

Code Maintenance XII

|  |  |  |
| --- | --- | --- |
| **Brief Description of Proposal:**  to make minor amendments including the correction of typographical errors, inconsistencies and formatting issues and updating of references. | | **Potentially affected Standards:**  Various standards |
| **Procedure:**  General | **Estimated total hours:**  Max 350 hours  Reasons why:  Limited or no economic impact, no need for an assessment of the risk to public health and safety. | **Estimated start work:**  May 2014 |

|  |
| --- |
| **Other Comments or Relevant Matters:**  This Proposal replaces Proposal P1032. The issues covered are identical to those that were to be included in P1032. However, following consideration of the issues, a number were determined to be outside the scope of the minor procedure. As FSANZ wished to progress those issues, P1032 has been abandoned and P1033 prepared under the general procedure so that those issues can proceed. |

***Decision***

|  |
| --- |
| **Proposal prepared**  Date: 27 May 2014 |

***Consultation & assessment timeframe***

|  |
| --- |
| **Proposed length of public consultation period:**  4 weeks |
| **Proposed timeframe for assessment:**  Commence assessment (clock start) Late May 2014  Completion of assessment & preparation of draft food reg measure Mid-June 2014  Public comment Mid-June-mid-July 2014  Board to complete approval Mid-Aug 2014  Notification to Forum Late Aug 2014  Anticipated gazettal if no review requested Early Nov 2014 |